## Issues
ID | Lane | Priority | Wave | Agent | Status | Title | Finding | Why it matters | Evidence | Spec anchors | Required changes | Acceptance | Proof | Touches
CCS-001 | current-live-blocker | P0 | W1 | constitutional-gate | in_progress | Replace advisory allow/deny booleans with a sealed execution capability | Execution authorization is represented as serializable booleans and a conventional `if` branch rather than a required capability. `EffectPreflightReportV1` exposes `blocked/advisory_only/commit_eligible`, `EffectCommitDecisionV1` exposes `commit_authorized`, `verification-policy` exposes `PolicyDecision::allows_execution() -> bool`, and `forge-pilot` branches on that boolean before calling execution. | This is policy by convention. A downstream caller can bypass the branch and still reach effectful code. The spec requires hard gates, not strongly-worded JSON. | effect-runtime/src/effect.rs; verification-policy/src/lib.rs:272; forge-pilot/src/loop_runner.rs:440,540,705; llm-tool-runtime/src/contracts.rs | V6 §2.8; V9 §5 and §11; V11 §8; ENDSTATE §8, §10, §17 | Introduce a sealed runtime-only `CommitToken` / `ExecutionPermit` minted only after policy + approval + verification-plan checks. All effectful execution APIs must require that token. Artifacts remain serializable receipts; the token is the runtime enforcement object. | No effectful path can be invoked with only booleans or raw strings. `rg -n "CommitToken¦ExecutionPermit¦ApprovalGrant" verification-policy llm-tool-runtime forge-pilot effect-runtime` returns owned types and use-sites; direct execute signatures without a permit are gone. | rg -n "allows_execution\(¦commit_authorized¦approval_token" effect-runtime verification-policy llm-tool-runtime forge-pilot && cargo test -p llm-tool-runtime -p forge-pilot | verification-policy/src/lib.rs; verification-policy/src/permit.rs (new); llm-tool-runtime/src/contracts.rs; llm-tool-runtime/src/runtime.rs; forge-pilot/src/loop_runner.rs; forge-pilot/src/act.rs; effect-runtime/src/effect.rs; stack-ids/src/ids.rs
CCS-002 | current-live-blocker | P0 | W1 | constitutional-gate | in_progress | Replace `ToolCtx.approval_token: Option<String>` with a typed constitutional grant | `llm-tool-runtime` already has decent enum discipline, but the actual approval carrier is still `Option<String>`. That means the critical approval path is stringly and forgeable by construction. | A free-form approval token undercuts the very enforcement point that should be strongest. It must be tied to scope, effect class, constitution citation, expiry, and decision lineage. | llm-tool-runtime/src/contracts.rs:262-291; llm-tool-runtime/src/runtime.rs:33-45; llm-tool-runtime/src/starter_tools.rs:401,493-514 | V9 §5 execution evidence; V11 §8 proof-governed promotion; V16 §8 budget/disclosure/suspension; ENDSTATE §8 and §10 | Define a typed `ApprovalGrant` or reuse the `CommitToken` family. Carry scope, effect/action class, approver lineage, expiry, decision id, and constitution citation. Read-only fast paths may remain tokenless only if the tool descriptor is provably read-only and non-promoting. | `ToolCtx` no longer contains `approval_token: Option<String>`. Approval evaluation accepts a typed grant. Destructive tools cannot be invoked with raw strings. | rg -n "approval_token: Option<String>" llm-tool-runtime/src && cargo test -p llm-tool-runtime | llm-tool-runtime/src/contracts.rs; llm-tool-runtime/src/runtime.rs; llm-tool-runtime/src/starter_tools.rs; forge-pilot/src/act.rs; verification-policy/src/lib.rs
CCS-003 | current-live-blocker | P0 | W2 | vocabulary-schema | in_progress | Eliminate stringly typed controlled vocabularies from governance and control surfaces | First-wave controlled vocabulary is now enum-backed across the execution, policy, attestation, review-control, delegation, continuity, adjudication, and remote-admission lanes: `effect-runtime` owns the execution vocab (`effect_class`, `blast_radius_ceiling`, `reversibility_class`, `run_mode`, `publication_status`, window/receipt/observation/result vocab), `verification-policy` now types the top-level policy profile vocab (`allowed_run_modes`/`required_preflight_checks`/`required_observation_classes`/`requires_compensation_plan_for`, `forbidden_role_combinations`, `required_assurance_sections`/`required_monitor_classes`, `required_forensic_freeze_surfaces`/`requires_postmortem_for_severity`), its `v14` budget/admission/disclosure vocab (`budget_class`/`max_exactness`/`refuter_allowance`/`oracle_allowance`/`replay_allowance`/`human_review_allowance`/`exhaustion_behavior`, `required_replayability_class`/`downgrade_behavior`, `replay_visibility`, `allowed_reveal_class`), plus the remaining privacy/locality policy lane (`default_retention_class`/`archive_restore_expectation`/`cross_border_transfer_default`, `approval_requirement`/`default_disclosure_budget_class`, `default_decision`, `disclosure_budget_class`/`export_package_format`, `tenant_key_kind`/`isolation_class`/`cross_tenant_query_default`, `required_attestation`/`required_disclosure_policy_class`); `assurance-runtime` now types `publication_status` plus `coverage_state`/`decision_state`/`status`/`trigger_kind`, `attestation-exchange` now types `replayability_class`/`expiration_policy`/`rotation_policy`/`admissibility_judgment` plus the vendor `translation_mode`/`rotation_channel`/`revocation_channel`/`replay_impact`/`admission_impact` lane, `authority-delegation` now types `blast_radius_ceiling`, `current_validity_state`, and `disclosure_ceiling`, `verification-control` now types review-case `final_state`/`block_reason`/`decision_state`, receipt `retry_owner`, and the v14 experiment/refuter/dispute lane (`risk_class`/`lifecycle_state`/`final_disposition`, `refuter_kind`/`state`/`promotion_impact`, `exactness_spend`/`selected_decision`, `current_disposition`, plus `admissibility_judgment`), `verification-adjudication` now types `rollback_scope`/`refutation_class`/`invalidation_radius` plus the v14 `decision_class`/`rollback_class` lane, `continuity-runtime` now types `severity`/`default_severity`/`status`/`replay_state`/`exercise_kind`, and `remote-oracle-admission` now types `exactness_class_ceiling`/`exactness_target`/`exactness_class` plus `disclosure_ceiling`/`allowed_disclosure`/`replay_obligation`/`local_admission_recommendation`/`failure_behavior`. The wider governance/policy/control crates still carry raw controlled vocabulary fields, so this row remains open. | Schemas will accept nonsense, exhaustive matching is impossible, and semantic drift becomes invisible at compile time. This is the opposite of constitutional enforcement. | `python3 scripts/check_constitutional_vocab.py` now passes and rejects raw `String`/`Vec<String>` declarations for the effect/policy/assurance/attestation/authority/review-control/adjudication/continuity/remote controlled-vocab lane. `effect-runtime/src/{effect,observation,compensation,vocab}.rs`, `verification-policy/src/{lib,v14,profile_p1_privacy,profile_p2_locality}.rs`, `assurance-runtime/src/{profile,assurance,certification}.rs`, `attestation-exchange/src/{lib,profile_p6_vendor}.rs`, `authority-delegation/src/capability.rs`, `verification-control/src/{lib,v14}.rs`, `verification-adjudication/src/{lib,v14}.rs`, `continuity-runtime/src/{incident,recovery,profile_p7_incident_routing,vocab}.rs`, and `remote-oracle-admission/src/lib.rs` now serialize controlled vocab with stable wire values; `profile-runtime/src/adapters.rs` explicitly bridges the typed policy vocab back to runtime-view strings; the stale `v14` examples in `examples/ExperimentCaseV1.example.json` and `examples/ComparabilityMatrixV1.example.json`, the top-level policy profile examples, and the privacy/locality policy examples now round-trip with those typed wire values; and the checked schemas/examples/fixtures remain compatible after regeneration. | V6 §2.8 and matrix law; V11 §3, §4, §6, §8; ENDSTATE §5, §7, §17 | Replace controlled vocabulary strings with enums in owner crates. Add serde-stable `snake_case` wire names. Introduce a repo lint that forbids new `String`-typed controlled vocab fields without an explicit allowlist annotation or script allowlist. | All controlled vocab fields are enum-backed or explicitly allowlisted as free text. `scripts/check_constitutional_vocab.py` passes and CI runs it. | rg -n "pub .*: String," effect-runtime assurance-runtime authority-delegation continuity-runtime remote-oracle-admission verification-policy verification-control verification-adjudication && python3 scripts/check_constitutional_vocab.py | effect-runtime/src/*.rs; assurance-runtime/src/*.rs; authority-delegation/src/*.rs; continuity-runtime/src/*.rs; remote-oracle-admission/src/*.rs; verification-policy/src/lib.rs; verification-control/src/lib.rs; verification-adjudication/src/lib.rs; contract-schema-gen/src/lib.rs; scripts/check_constitutional_vocab.py (new)
CCS-004 | current-live-blocker | P0 | W2 | vocabulary-schema | in_progress | Add builders and `validate()` invariants to effect and governance artifact families | `effect-runtime`, `verification-policy`, `assurance-runtime`, `authority-delegation`, `attestation-exchange`, `verification-control`, `verification-adjudication`, `continuity-runtime`, and `remote-oracle-admission` no longer behave like pure passive type surfaces: owner-side `new`/`validate()` paths now enforce schema versions, duplicate typed-policy vocab bans, privacy/locality policy invariants, delegation depth/TTL bounds, permit/approval coherence, review-case citation/obligation closure, policy `v14` experiment/refuter/disclosure invariants, control `v14` experiment/refuter/dispute invariants, rollout/rollback geometry coherence, vendor/trust-root invariants, continuity incident/recovery clocks, and remote slice/replay citation requirements. The broader governance family still lacks equivalent builders and validators, so the row remains open. | Schema conformance is not semantic conformance. Without owner-side builders and `validate()` methods, impossible states remain easy to construct. | `cargo test -p effect-runtime -p assurance-runtime -p authority-delegation -p attestation-exchange -p continuity-runtime -p remote-oracle-admission -p verification-control -p verification-adjudication -p verification-policy -p profile-runtime` now covers constructor/validator paths, fixture validation, adapter compatibility, and impossible-state rejection across the effect, policy, assurance, authority, attestation, review-control, continuity, adjudication, remote-admission, and composition surfaces. `verification-policy/src/{lib,v14,profile_p1_privacy,profile_p2_locality}.rs`, `continuity-runtime/src/{incident,recovery,slo,profile_p7_incident_routing}.rs`, `attestation-exchange/src/{lib,profile_p6_vendor}.rs`, `verification-control/src/{lib,v14}.rs`, `verification-adjudication/src/{lib,v14}.rs`, and `remote-oracle-admission/src/lib.rs` now own top-level constructor/validator entry points for policy profiles, privacy/locality policy artifacts, approvals/decisions, `v14` experiment budgets and admission/disclosure policy, review-case closure, v14 experiment/refuter/dispute and rollout/rollback validation, incident/recovery, trust-root/vendor, and lease/request/result/replay artifacts; `profile-runtime/src/adapters.rs` proves the typed policy lane still composes into runtime-view obligations; the example validation tests in `verification-policy/tests/{policy_profile_example_roundtrip,v14_example_roundtrip,profile_p1_example_roundtrip,profile_p2_example_roundtrip,v25_policy_citation_flow}.rs`, `verification-control/tests/{v14_example_roundtrip,v25_review_case_roundtrip}.rs`, and `verification-adjudication/tests/{v14_example_roundtrip,v25_example_roundtrip}.rs` keep those surfaces honest; and `python3 scripts/check_public_api_docs.py` reports `verification-control` at 36/36 and `verification-policy` at 49/49 documented public functions. | V9 §11 schema governance and reference-interpreter law; V11 §5 reference interpreters and semantic conformance; ENDSTATE §17.1-17.2 | For each owner crate, add `validate()` plus builders that enforce mandatory citations, obligation refs, advisory rules, decision/receipt chain integrity, and cross-field invariants. Generate fixtures from builders, not handwritten JSON only. | Every constitutional artifact family has owner-side validation. Handwritten impossible states fail validation. Cross-crate fixtures round-trip through builders and validators. | rg -n "fn validate\(¦impl .*Builder¦new\(" effect-runtime assurance-runtime authority-delegation continuity-runtime remote-oracle-admission attestation-exchange && cargo test -p effect-runtime -p assurance-runtime -p authority-delegation -p continuity-runtime | effect-runtime/src/*.rs; assurance-runtime/src/*.rs; attestation-exchange/src/lib.rs; authority-delegation/src/*.rs; continuity-runtime/src/*.rs; remote-oracle-admission/src/*.rs; tests/fixtures in corresponding crates
CCS-005 | current-live-blocker | P0 | W3 | proof-conformance | open | Implement reference interpreters for hard semantic seams and wire differential conformance | The repo has real artifact families and some strong bridge tests, but the hard seams are still not formally owned as reference interpreters: execution admissibility, widening/degradation semantics, minimal-change repair, and effect decision chain validity. | Without reference interpreters, semantics can drift while schemas stay green. Bridge atomicity is partly enforced already; the rest of the hard seams need the same treatment. | Bridge tests already reject missing `episode_id` for canonical bundle-bearing exports (`forge-memory-bridge/src/transform.rs` and tests). Comparable reference modules are missing for execution admissibility, widening, and repair. The current `conformance/` tree holds manifests/README surfaces but not a unified hard-seam refint harness. | V9 §11; V11 §5.1-5.4; V12 §5-§7; ENDSTATE §17 | Add explicit reference-interpreter modules for: (a) preflight→commit→execution admissibility, (b) widening/degradation outcome classification, (c) minimal-change repair selection, (d) import atomicity / episode bundle requirements. Wire them into `kernel-conformance` and `conformance/*` differential tests. | Every hard seam has a reference implementation, golden fixtures, and production-vs-refint differential tests. Semantic drift budget is explicit and gated. | rg -n "refint¦reference interpreter¦differential" kernel-conformance conformance verification-policy verification-adjudication knowledge-runtime forge-memory-bridge && cargo test -p kernel-conformance -p verification-policy -p forge-memory-bridge | kernel-conformance/src or tests; conformance/*; verification-policy/src/*; knowledge-runtime/src/*; verification-adjudication/src/*; forge-memory-bridge/src/*
CCS-006 | current-live-blocker | P0 | W3 | release-hardening | in_progress | Promote constitutional lints and proof checks into the front-door gate and CI | `make gate` and CI now run permit-path enforcement, the widened constitutional vocab lint, and mandatory artifact-ref enforcement, so direct effect execution without typed permits, raw controlled-vocab `String`/`Vec<String>` fields, promotable loop reports that stop carrying verification-plan artifacts, remote slice artifacts that skip required refs, and canonical bundle transforms that skip `episode_id` lineage all fail the front door. Generated-surface admission and endstate-family coverage-claim lints are still missing, so the row remains in progress. | If the gates do not enforce the constitution, the constitution is advisory paperwork. | `scripts/check_commit_permit_paths.py`, `scripts/check_constitutional_vocab.py`, and the new `scripts/check_mandatory_artifact_refs.py` are wired through `scripts/release_gate_set.py`, exercised by `make gate`, and inherited by `.github/workflows/ci.yml` via `make gate`. The mandatory-ref gate locks in non-optional `PolicyDecision.plan_id`, permit minting rejection for advisory-only or non-promotable plans, `forge-pilot` verification-plan artifact emission, `remote-oracle-admission` required/returned artifact refs, `effect-runtime` initiating/execution lineage refs, and `forge-memory-bridge` rejection of canonical bundle exports missing `episode_id`; the vocab lint still covers the additional `verification-policy` privacy/locality controlled fields; the docs gate reports `verification-policy` at 49/49 documented public functions; and the gate is green after rerunning the full release-lane test sweep. | V6 crate/plane implications; V11 §12 release bar; ENDSTATE §17.3-17.4 | Keep the permit, vocab, and mandatory artifact-ref scripts wired into `make gate` and CI, then add the remaining generated-surface admission and endstate-family coverage-claim gates before any closure claim. | `make gate` and CI fail on raw approval strings, direct effect execution without a permit, missing verification plans or mandatory artifact refs, or uncontrolled vocabulary strings. | sed -n '1,220p' Makefile && sed -n '1,220p' .github/workflows/ci.yml && python3 scripts/check_constitutional_vocab.py && python3 scripts/check_commit_permit_paths.py && python3 scripts/check_mandatory_artifact_refs.py | Makefile; .github/workflows/ci.yml; scripts/run_release_gates.py; scripts/check_constitutional_vocab.py; scripts/check_commit_permit_paths.py; scripts/check_mandatory_artifact_refs.py (new)
CCS-007 | current-live-hardening | P1 | W4 | surface-rationalization | open | Rationalize crate names so ‘runtime’ means runtime and ‘surface’ means typed contract surface | Several crates now explicitly describe themselves as typed surface crates rather than runtimes, but their package names still advertise runtime behavior: `assurance-runtime`, `continuity-runtime`, `remote-oracle-admission`, `spec-execution`, and others. | This confuses reviewers and encourages over-claiming. A constitutional stack must be truthful at the package boundary. | README/lib headers in these crates say ‘typed ... surface crate’ while package names still say runtime/execution/admission. | V6 authority map; V11 §11 crate and plane implications; ENDSTATE §16 crate responsibility map | Either rename the crates/packages to `*-surface` / `*-contracts`, or keep the compatibility names but add front-door documentation and package metadata that unambiguously states they are bounded surface crates. Do not leave ambiguous names. | A new reader can tell from Cargo metadata and README whether a crate is a runtime, a surface crate, or a helper evaluator. | rg -n "typed .* surface crate¦not a .* runtime¦compatibility name" assurance-runtime attestation-exchange continuity-runtime remote-oracle-admission spec-execution federated-settlement mechanism-runtime | Cargo.toml files; crate READMEs/lib.rs docs; PACK_README/README surfaces
CCS-008 | current-live-hardening | P1 | W4 | surface-rationalization | open | Remove or archive scaffolds that shadow production crate names | The repo carries 17 scaffold directories that duplicate production crate names. Auditors can easily read the wrong implementation surface. | Shadow copies corrode trust and make evidence ambiguous. | `scaffolds/` duplicates: attestation-exchange, constraint-compiler, contract-schema-gen, forge-memory-bridge, forge-pilot, kernel-conformance, kernel-execution, kernel-oracles, knowledge-runtime, llm-tool-runtime, remote-oracle-admission, semantic-memory, semantic-memory-forge, stack-ids, verification-adjudication, verification-control, verification-policy | V6 anti-shadow rule; ENDSTATE §2.13 no shadow databases and no shadow constitutions | Move scaffolds out of the active repo surface (archive branch, separate repo, or docs archive) and make the production tree the only authoritative implementation surface. | No scaffold directory shadows a production crate name in the working tree. | find scaffolds -maxdepth 1 -mindepth 1 -type d | scaffolds/**; docs/archive/**; PACK_MANIFEST/README
CCS-009 | current-live-hardening | P1 | W4 | surface-rationalization | open | Resolve the `living-memory` vs `forge-engine` naming split | The path is `living-memory/living-memory`, the package name is `forge-engine`, and the README/lib docs say `forge-engine`. | A core crate should not present three names. It complicates audit, ownership, and release messaging. | living-memory/living-memory/Cargo.toml; living-memory/living-memory/README.md; living-memory/living-memory/src/lib.rs; living-memory/BUILD_SHEET.md | V11 §11.13; ENDSTATE §16 | Pick one externally visible name and use it consistently across path, Cargo package, README, and docs. If compatibility requires an alias, document it explicitly and briefly. | The crate has one canonical external name and one documented compatibility alias at most. | rg -n "forge-engine¦living-memory" living-memory | living-memory/**; workspace Cargo references; README/front-door docs
CCS-010 | current-live-hardening | P1 | W4 | surface-rationalization | in_progress | Split hotspot files in the operationally critical lane | Review hotspots remain concentrated in large files: `profile-runtime/src/adapters.rs` (1775 LOC), `living-memory/living-memory/src/lab/evidence.rs` (1617), `semantic-memory/src/db.rs` (1608), `semantic-memory/src/lib.rs` (1599), `forge-pilot/src/main_support/mod.rs` (1591), `semantic-memory/src/search.rs` (1582), and `semantic-memory-forge/src/envelope.rs` (1393). `forge-pilot/src/loop_runner.rs` has been reduced to 952 LOC and now clears the release gate, but the remaining files still exceed budget. | These files sit on the constitutional path. Giant files hide defects and slow hostile review. | Current repo line scan over Rust sources; `python3 scripts/check_hotspot_budgets.py`/`bash scripts/check_hotspot_budgets.sh` now pass after extracting `forge-pilot/src/loop_runner_helpers.rs`. | V11 §12 release bar; ENDSTATE §17 required test tracks (maintainability is a precondition for reliable conformance) | Refactor by concern boundary, not by arbitrary slicing. Separate admission, execution, reporting, repair, and persistence seams into smaller modules with targeted tests. | No constitutional hotspot file exceeds the agreed LOC threshold (recommend 900 LOC hard cap, 700 soft cap) without an explicit waiver. | python3 scripts/check_hotspot_budgets.py | forge-pilot/src/main_support/mod.rs; forge-pilot/src/loop_runner.rs; profile-runtime/src/adapters.rs; semantic-memory/src/db.rs; semantic-memory/src/lib.rs; semantic-memory/src/search.rs; semantic-memory-forge/src/envelope.rs; living-memory/living-memory/src/lab/evidence.rs
CCS-011 | current-live-hardening | P1 | W3 | proof-conformance | open | Expand kernel tests from existence proofs to failure-surface coverage | The hostile zero-test claim is stale, but the kernel lane still needs focused tests for oscillation, budget exhaustion, negative updates, and pathological residual behavior. | The kernel is the exact place where silent wrongness becomes expensive. | Current test markers: kernel-oracles 13, kernel-execution 10, recursive-kernel-core 3. These are real, but not enough for full constitutional confidence. | V11 §4.2-§4.5, §5.3; V12 §6; ENDSTATE §7 and §17.3 | Add property tests and deterministic fixtures for empty graphs, single-node graphs, oscillation boundaries, budget exhaustion, contradiction preservation under widening, and witness/refuter edge cases. | Kernel crates have dedicated failure-surface tests and property tests; regression fixtures cover bounded exact vs degraded outcomes. | rg -n "budget¦oscillat¦widen¦residual¦refut¦witness" kernel-oracles kernel-execution recursive-kernel-core tests && cargo test -p kernel-oracles -p kernel-execution -p recursive-kernel-core | kernel-oracles/src/lib.rs or tests; kernel-execution/src/lib.rs or tests; recursive-kernel-core/src/lib.rs or tests; kernel-conformance/tests/*
CCS-012 | current-live-hardening | P1 | W3 | proof-conformance | in_progress | Add impossible-to-bypass blocked-execution end-to-end tests | Denied, advisory-only, out-of-scope, expired, and mismatched-effect execution paths now have real coverage across `llm-tool-runtime`, `verification-policy`, and `forge-pilot`, and `verification-policy` now carries a compile-fail doctest proving the sealed `CommitToken` cannot be forged outside the owner crate. The bypass matrix is materially stronger, but the row stays in progress until the broader bypass combinations are exhausted. | The whole advisory-vs-enforcement gap closes only when bypass attempts fail automatically. | `llm-tool-runtime` now has runtime tests for missing permit, missing typed grant, out-of-scope permit, out-of-scope grant, expired grant, and mismatched-effect grant denial; `verification-policy/tests/v25_policy_citation_flow.rs` proves advisory-only plans cannot mint execution permits; `forge-pilot/tests/verification_control_tests.rs` proves policy-denied and advisory-only paths do not execute actions; and the `compile_fail` doctest on `verification-policy/src/permit.rs` proves `CommitToken` construction is not available outside the owner crate. | V11 §8.3 consumer-only orchestrator law; ENDSTATE §10 and §17 | Keep extending the bypass matrix so blocked execution stays unreachable across additional forged-lineage, decision-mismatch, and harness-level bypass attempts, not just the first denied/advisory/expired/scope/effect paths. | Blocked execution cannot be reached in test harnesses, even when callers attempt to bypass normal orchestration code. | cargo test -p llm-tool-runtime -p forge-pilot -p verification-policy && cargo test -p verification-control | llm-tool-runtime/tests/*; forge-pilot/tests/*; verification-policy/tests/*; verification-control/tests/*
CCS-013 | current-live-hardening | P1 | W4 | proof-conformance | open | Reduce unwrap/expect concentration in Primitives and operational hot paths | The `Primitives` family still carries a large number of `unwrap/expect` calls, especially in `cea-sqlite`, `sandbox-workspace`, and `check-runner`. The exact count in the current snapshot is higher than the hostile text claimed because the tree has moved. | Panics in persistence, process management, or sandbox logic are production faults waiting to happen. | Current snapshot count across packaged `Primitives/*` crates is 222 unwrap/expect calls; `Primitives/cea-sqlite` alone has 77; `Primitives/check-runner` contains the only `unsafe` blocks. | V6 reliability layer; V11 failure artifacts; ENDSTATE §17.3 required test tracks | Triage and replace panic sites in I/O, DB, and process-management paths with typed errors. Keep explicit, justified panic sites only in tests or impossible-invariant guards with comments. | Production panic inventory is intentionally small, reviewed, and documented. Hot paths no longer panic on recoverable operational errors. | rg -n "\.unwrap\(¦\.expect\(" Primitives semantic-memory forge-pilot knowledge-runtime && bash scripts/check_no_prod_panics.sh | Primitives/**; semantic-memory/**; forge-pilot/**; scripts/check_no_prod_panics.sh
CCS-014 | current-live-hardening | P2 | W4 | surface-rationalization | open | Replace or strictly fence the brittle line-based Rust symbol extractor | `forge-pilot/src/bootstrap/extract/rust.rs` still relies on prefix-based line parsing. | Fast is fine; undefined extraction semantics are not. If this stays, the limitation must be explicit and fail-closed. | forge-pilot/src/bootstrap/extract/rust.rs | V6 parser/patch reliability layer; ENDSTATE §18 explicit prohibitions (no silent approximation) | Either replace it with a parser-backed extractor or force it behind explicit degraded-mode markers, scope limits, and tests that prove it fails closed on unsupported syntax. | Unsupported Rust syntax cannot silently produce canonical artifacts. | cargo test -p forge-pilot -- bootstrap && rg -n "degraded¦unsupported" forge-pilot/src/bootstrap/extract/rust.rs | forge-pilot/src/bootstrap/extract/rust.rs; forge-pilot/tests/*; docs/limitations.md or equivalent
CCS-015 | full-spec-gap | P2 | W5 | endstate-runtime | open | Implement the missing v12 regional runtime artifact families and scheduling law | The current repo does not expose `RegionContractV1`, `DeltaEnvelopeV1`, `ResidualEnvelopeV1`, `SyndromeEnvelopeV1`, `RegionBoundaryReceiptV1`, `RegionConvergenceReportV1`, or `RegionExactnessBudgetV1` surfaces. | You cannot claim full v12 / endstate conformance without typed regional execution units and boundary protocols. | No hits for these artifact names in the current tree. | V12 §4-§11; ENDSTATE §11 | Add the missing artifact families, IDs, schemas, builders/validators, and bounded evaluators. Wire them into scheduler/planner logic and conformance fixtures. | All mandatory v12 regional artifact families exist, validate, serialize, and participate in conformance tests and release gates. | rg -n "RegionContractV1¦DeltaEnvelopeV1¦ResidualEnvelopeV1¦SyndromeEnvelopeV1¦RegionBoundaryReceiptV1¦RegionConvergenceReportV1¦RegionExactnessBudgetV1" semantic-memory-forge stack-ids knowledge-runtime kernel-execution contract-schema-gen conformance | semantic-memory-forge/src/v12.rs (new); stack-ids/src/ids.rs; contract-schema-gen/src/lib.rs; knowledge-runtime/**; kernel-execution/**; conformance/v12/**
CCS-016 | full-spec-gap | P2 | W5 | endstate-runtime | open | Implement typed local repair, nuisance-state, and cross-boundary replay families | The current repo has witnesses/syndromes and some repair receipts, but the v12 families for `RepairCandidateBundleV1`, `NuisanceEnvelopeV1`, and `RegionReplaySliceV1` are not exposed as canonical artifact families. | Local repair before global rebuild is constitutional law, not a comment. Nuisance state and replay slices must be typed. | No hits for `RepairCandidateBundleV1`, `NuisanceEnvelopeV1`, or `RegionReplaySliceV1` in the current tree. | V12 §7-§9; ENDSTATE §10-§12 | Add the missing families and connect them to repair selection, replay queries, and regional runtime decisions. | Repair, nuisance, and replay work show up as typed artifacts with validators and conformance fixtures. | rg -n "RepairCandidateBundleV1¦NuisanceEnvelopeV1¦RegionReplaySliceV1" semantic-memory-forge verification-adjudication knowledge-runtime contract-schema-gen conformance | semantic-memory-forge/src/v12.rs (new); verification-adjudication/**; knowledge-runtime/**; conformance/v12/**
CCS-017 | full-spec-gap | P2 | W5 | endstate-runtime | open | Finish treaty/quorum/challenge closure in federated settlement | `federated-settlement` already has bounded evaluators, but the full v16 law is not closed: explicit evidentiary quorum profiles, challenge lanes, and richer replay/publication enforcement remain incomplete. | Bounded evaluators are not full treaty runtime closure. | `federated-settlement/src/lib.rs` has `evaluate_shared_replay`, `evaluate_divergence_or_suspension`, and `evaluate_settlement`, but the broader v16 families and challenge/quorum machinery are not all present. | V16 §6-§8, §12; ENDSTATE §14 | Add missing artifact families and conformance tracks for quorum, challenge, shared publication, and replay enforcement. Preserve local dissent at every promotion boundary. | Shared settlement cannot bypass missing replay, blocking dissent, or quorum requirements; all paths emit typed downgrade/suspension artifacts. | rg -n "EvidentiaryQuorumProfileV1¦SharedViewPublicationV1¦challenge" federated-settlement contract-schema-gen conformance/v16 && cargo test -p federated-settlement | federated-settlement/src/lib.rs; tests/*; contract-schema-gen/src/lib.rs; conformance/v16/**
CCS-018 | full-spec-gap | P2 | W5 | endstate-runtime | open | Finish theory publication / refuter / identifiability closure in mechanism runtime | `mechanism-runtime` already blocks local review on missing refuters or stability problems, but it does not yet close the full v17 lane around publication decisions, dispute bundles, identifiability reports, and retirement/supersession. | No score-only theory publication is constitutional law. The current helper evaluator is a start, not the finish. | `mechanism-runtime/src/lib.rs` exposes `evaluate_fit_run`, but the broader v17 artifact set is incomplete. | V17 §7-§9, §13; ENDSTATE §13 | Add identifiability, theory publication decision, dispute/supersession/retirement families and conformance gates. Require typed refuter suites before any non-advisory publication step. | Theory publication remains impossible without typed refuter and stability evidence; dispute and retirement are first-class artifact families. | rg -n "TheoryPublicationDecisionV1¦IdentifiabilityReportV1¦TheoryDisputeBundleV1¦TheorySupersessionV1¦TheoryRetirementV1" mechanism-runtime contract-schema-gen conformance/v17 && cargo test -p mechanism-runtime | mechanism-runtime/src/lib.rs; tests/*; contract-schema-gen/src/lib.rs; conformance/v17/**
CCS-019 | full-spec-gap | P2 | W6 | endstate-runtime | open | Implement lawful subtraction families and proofs | The current tree has no `SupportCore`, `RemovalFrontier`, `InvariantPreservationReceipt`, or `HistoricalLossBudget` families. | You cannot claim endstate conformance without challengeable forgetting/compaction/subtraction. | No hits for these artifact names in the current tree. | ENDSTATE §9 and §12 | Define the subtraction families, add IDs/schemas/validators, and implement bounded subtraction with invariant preservation receipts and historical loss budgets. | Subtractive operations emit first-class artifacts and cannot silently discard epistemic support. | rg -n "SupportCore¦RemovalFrontier¦InvariantPreservationReceipt¦HistoricalLossBudget" semantic-memory-forge semantic-memory knowledge-runtime kernel-conformance contract-schema-gen conformance | semantic-memory-forge/src/subtraction.rs (new); stack-ids/src/ids.rs; semantic-memory/**; knowledge-runtime/**; kernel-conformance/**; conformance/endstate/**
CCS-020 | full-spec-gap | P2 | W6 | endstate-runtime | open | Close the constitutional self-hosting loop with proof/veto/challenge enforcement | `spec-execution` has generated schema/interpreter/proof artifacts and helper evaluators, but generated surfaces are not yet wired through a mandatory end-to-end admission/veto/challenge closure. | Generated is not admitted. The constitution must prove that at runtime, not just say it. | `spec-execution/src/lib.rs` exposes generation helpers and governance states, but full end-to-end closure remains surface-level. | V11 §5, §8; ENDSTATE §15 and §17 | Add end-to-end self-hosting workflows that require proof evaluation, human veto/challenge consideration, and explicit admission receipts before generated surfaces can affect runtime behavior. | Generated schemas/interpreters remain non-admitted until proof, veto, and challenge workflows clear; this is tested and gated. | rg -n "HumanVetoBundleV1¦MetaChallengeBundleV1¦SelfHostingBuildReceiptV1¦admission_allowed" spec-execution conformance && cargo test -p spec-execution | spec-execution/src/lib.rs; tests/*; conformance/v20/**; scripts/check_generated_surface_admission.py (new)

## Reconciled
ID | Title | Status | Finding | Evidence | Proof
REC-001 | `kernel-oracles` zero-tests claim is stale for this snapshot | reconciled | The current archive contains inline tests in `kernel-oracles`; the crate is not testless. | 13 current test markers in `kernel-oracles/src/lib.rs`. | rg -n "#\[test\]¦proptest!¦tokio::test" kernel-oracles/src
REC-002 | `kernel-execution` zero-tests claim is stale for this snapshot | reconciled | The current archive contains inline tests in `kernel-execution`; the crate is not testless. | 10 current test markers in `kernel-execution/src/lib.rs`. | rg -n "#\[test\]¦proptest!¦tokio::test" kernel-execution/src
REC-003 | `recursive-kernel-core` zero-tests claim is stale for this snapshot | reconciled | The current archive contains inline tests in `recursive-kernel-core`; the crate is not testless. | 3 current test markers in `recursive-kernel-core/src/lib.rs`. | rg -n "#\[test\]¦proptest!¦tokio::test" recursive-kernel-core/src
REC-004 | ‘CI is folklore / absent’ is stale for this snapshot | reconciled | The current repo does have a GitHub Actions workflow and a `make gate` surface. | `.github/workflows/ci.yml` exists and runs `make gate` plus v25 closure checks. | test -f .github/workflows/ci.yml && sed -n '1,220p' .github/workflows/ci.yml
REC-005 | ‘The repo is mostly shells and no real system’ is overstated for this snapshot | reconciled | The core lane is substantial: `semantic-memory`, `living-memory/forge-engine`, `knowledge-runtime`, `forge-pilot`, `semantic-memory-forge`, and `forge-memory-bridge` are real systems with deep test/doc surfaces. | Current metrics show hundreds of test markers/docs/public fns in the core lane, even though enforcement gaps remain. | See crate metrics sheet in the workbook and `01_SOURCE_BASIS_AND_RECONCILIATION.md`.

## TouchMap
Issue | Wave | Priority | Path
CCS-001 | W1 | P0 | verification-policy/src/lib.rs
CCS-001 | W1 | P0 | verification-policy/src/permit.rs (new)
CCS-001 | W1 | P0 | llm-tool-runtime/src/contracts.rs
CCS-001 | W1 | P0 | llm-tool-runtime/src/runtime.rs
CCS-001 | W1 | P0 | forge-pilot/src/loop_runner.rs
CCS-001 | W1 | P0 | forge-pilot/src/act.rs
CCS-001 | W1 | P0 | effect-runtime/src/effect.rs
CCS-001 | W1 | P0 | stack-ids/src/ids.rs
CCS-002 | W1 | P0 | llm-tool-runtime/src/contracts.rs
CCS-002 | W1 | P0 | llm-tool-runtime/src/runtime.rs
CCS-002 | W1 | P0 | llm-tool-runtime/src/starter_tools.rs
CCS-002 | W1 | P0 | forge-pilot/src/act.rs
CCS-002 | W1 | P0 | verification-policy/src/lib.rs
CCS-003 | W2 | P0 | effect-runtime/src/*.rs
CCS-003 | W2 | P0 | assurance-runtime/src/*.rs
CCS-003 | W2 | P0 | authority-delegation/src/*.rs
CCS-003 | W2 | P0 | continuity-runtime/src/*.rs
CCS-003 | W2 | P0 | remote-oracle-admission/src/*.rs
CCS-003 | W2 | P0 | verification-policy/src/lib.rs
CCS-003 | W2 | P0 | verification-control/src/lib.rs
CCS-003 | W2 | P0 | verification-adjudication/src/lib.rs
CCS-003 | W2 | P0 | contract-schema-gen/src/lib.rs
CCS-003 | W2 | P0 | scripts/check_constitutional_vocab.py (new)
CCS-004 | W2 | P0 | effect-runtime/src/*.rs
CCS-004 | W2 | P0 | assurance-runtime/src/*.rs
CCS-004 | W2 | P0 | attestation-exchange/src/lib.rs
CCS-004 | W2 | P0 | authority-delegation/src/*.rs
CCS-004 | W2 | P0 | continuity-runtime/src/*.rs
CCS-004 | W2 | P0 | remote-oracle-admission/src/*.rs
CCS-004 | W2 | P0 | tests/fixtures in corresponding crates
CCS-005 | W3 | P0 | kernel-conformance/src or tests
CCS-005 | W3 | P0 | conformance/*
CCS-005 | W3 | P0 | verification-policy/src/*
CCS-005 | W3 | P0 | knowledge-runtime/src/*
CCS-005 | W3 | P0 | verification-adjudication/src/*
CCS-005 | W3 | P0 | forge-memory-bridge/src/*
CCS-006 | W3 | P0 | Makefile
CCS-006 | W3 | P0 | .github/workflows/ci.yml
CCS-006 | W3 | P0 | scripts/run_release_gates.py
CCS-006 | W3 | P0 | scripts/check_constitutional_vocab.py (new)
CCS-006 | W3 | P0 | scripts/check_commit_permit_paths.py (new)
CCS-006 | W3 | P0 | scripts/check_mandatory_artifact_refs.py (new)
CCS-007 | W4 | P1 | Cargo.toml files
CCS-007 | W4 | P1 | crate READMEs/lib.rs docs
CCS-007 | W4 | P1 | PACK_README/README surfaces
CCS-008 | W4 | P1 | scaffolds/**
CCS-008 | W4 | P1 | docs/archive/**
CCS-008 | W4 | P1 | PACK_MANIFEST/README
CCS-009 | W4 | P1 | living-memory/**
CCS-009 | W4 | P1 | workspace Cargo references
CCS-009 | W4 | P1 | README/front-door docs
CCS-010 | W4 | P1 | forge-pilot/src/main_support/mod.rs
CCS-010 | W4 | P1 | forge-pilot/src/loop_runner.rs
CCS-010 | W4 | P1 | profile-runtime/src/adapters.rs
CCS-010 | W4 | P1 | semantic-memory/src/db.rs
CCS-010 | W4 | P1 | semantic-memory/src/lib.rs
CCS-010 | W4 | P1 | semantic-memory/src/search.rs
CCS-010 | W4 | P1 | semantic-memory-forge/src/envelope.rs
CCS-010 | W4 | P1 | living-memory/living-memory/src/lab/evidence.rs
CCS-011 | W3 | P1 | kernel-oracles/src/lib.rs or tests
CCS-011 | W3 | P1 | kernel-execution/src/lib.rs or tests
CCS-011 | W3 | P1 | recursive-kernel-core/src/lib.rs or tests
CCS-011 | W3 | P1 | kernel-conformance/tests/*
CCS-012 | W3 | P1 | llm-tool-runtime/tests/*
CCS-012 | W3 | P1 | forge-pilot/tests/*
CCS-012 | W3 | P1 | verification-policy/tests/*
CCS-012 | W3 | P1 | verification-control/tests/*
CCS-013 | W4 | P1 | Primitives/**
CCS-013 | W4 | P1 | semantic-memory/**
CCS-013 | W4 | P1 | forge-pilot/**
CCS-013 | W4 | P1 | scripts/check_no_prod_panics.sh
CCS-014 | W4 | P2 | forge-pilot/src/bootstrap/extract/rust.rs
CCS-014 | W4 | P2 | forge-pilot/tests/*
CCS-014 | W4 | P2 | docs/limitations.md or equivalent
CCS-015 | W5 | P2 | semantic-memory-forge/src/v12.rs (new)
CCS-015 | W5 | P2 | stack-ids/src/ids.rs
CCS-015 | W5 | P2 | contract-schema-gen/src/lib.rs
CCS-015 | W5 | P2 | knowledge-runtime/**
CCS-015 | W5 | P2 | kernel-execution/**
CCS-015 | W5 | P2 | conformance/v12/**
CCS-016 | W5 | P2 | semantic-memory-forge/src/v12.rs (new)
CCS-016 | W5 | P2 | verification-adjudication/**
CCS-016 | W5 | P2 | knowledge-runtime/**
CCS-016 | W5 | P2 | conformance/v12/**
CCS-017 | W5 | P2 | federated-settlement/src/lib.rs
CCS-017 | W5 | P2 | tests/*
CCS-017 | W5 | P2 | contract-schema-gen/src/lib.rs
CCS-017 | W5 | P2 | conformance/v16/**
CCS-018 | W5 | P2 | mechanism-runtime/src/lib.rs
CCS-018 | W5 | P2 | tests/*
CCS-018 | W5 | P2 | contract-schema-gen/src/lib.rs
CCS-018 | W5 | P2 | conformance/v17/**
CCS-019 | W6 | P2 | semantic-memory-forge/src/subtraction.rs (new)
CCS-019 | W6 | P2 | stack-ids/src/ids.rs
CCS-019 | W6 | P2 | semantic-memory/**
CCS-019 | W6 | P2 | knowledge-runtime/**
CCS-019 | W6 | P2 | kernel-conformance/**
CCS-019 | W6 | P2 | conformance/endstate/**
CCS-020 | W6 | P2 | spec-execution/src/lib.rs
CCS-020 | W6 | P2 | tests/*
CCS-020 | W6 | P2 | conformance/v20/**
CCS-020 | W6 | P2 | scripts/check_generated_surface_admission.py (new)

## CrateMetrics
Crate | Source lines | Pub fns | Doc comments | Test markers | String fields | Enum defs | unwrap/expect
effect-runtime | 677 | 0 | 10 | 3 | 53 | 0 | 48
verification-policy | 1253 | 6 | 7 | 19 | 84 | 2 | 67
verification-control | 2446 | 20 | 20 | 16 | 76 | 14 | 57
assurance-runtime | 494 | 0 | 4 | 12 | 94 | 0 | 61
attestation-exchange | 200 | 0 | 4 | 5 | 35 | 0 | 23
authority-delegation | 367 | 0 | 4 | 7 | 69 | 0 | 38
continuity-runtime | 369 | 0 | 4 | 7 | 80 | 0 | 38
remote-oracle-admission | 193 | 0 | 0 | 1 | 32 | 0 | 0
mechanism-runtime | 334 | 1 | 5 | 4 | 16 | 1 | 4
spec-execution | 526 | 3 | 5 | 4 | 28 | 2 | 7
federated-settlement | 617 | 3 | 5 | 7 | 37 | 2 | 12
kernel-oracles | 1006 | 8 | 8 | 13 | 6 | 3 | 7
kernel-execution | 1216 | 7 | 7 | 10 | 9 | 5 | 1
recursive-kernel-core | 256 | 4 | 4 | 3 | 9 | 7 | 2
llm-tool-runtime | 2470 | 32 | 31 | 11 | 24 | 13 | 13
forge-pilot | 12780 | 114 | 59 | 55 | 91 | 21 | 168
semantic-memory-forge | 4865 | 34 | 362 | 47 | 131 | 27 | 134
forge-memory-bridge | 3419 | 10 | 329 | 44 | 33 | 9 | 72
semantic-memory | 28992 | 119 | 1115 | 303 | 156 | 16 | 930
knowledge-runtime | 10778 | 73 | 835 | 145 | 57 | 18 | 364
living-memory/living-memory | 15977 | 137 | 802 | 181 | 154 | 26 | 371
profile-runtime | 3952 | 43 | 49 | 13 | 56 | 4 | 66

## CrateRoles
Crate | Role | Constitutional note
stack-ids | IDs and typed vocab roots | Keep IDs pure; add permit IDs if needed, but do not turn it into a junk drawer.
semantic-memory-forge | Canonical artifact families | Own new v12/vendstate family types and validators.
forge-memory-bridge | Export/import transform and import atomicity | Reference interpreter and differential tests for import atomicity.
semantic-memory | Projection and queryable truth | Must stay authoritative for projected truth; add subtraction families carefully.
knowledge-runtime | View/routing/planning runtime | Must surface widening and consume only admitted artifacts.
verification-policy | Policy evaluation and permit minting | Own `CommitToken`/`ApprovalGrant` minting and policy validity.
verification-control | Control receipts, proofs, and release-facing evidence | Consume permits and publish control receipts.
effect-runtime | Effect artifact contracts | Must gain builders/validators and stop being pure type scaffolding.
llm-tool-runtime | Tool execution runtime | Must consume typed grants, not raw approval strings.
forge-pilot | Orchestrator | May never bypass permit gating or silently widen to green.
kernel-execution | Regional/kernel execution | Needs failure-surface tests and eventual v12 regional artifacts.
kernel-oracles | Refutation/oracle slices | Needs stronger failure-surface tests and integration with proof ladders.
federated-settlement | Treaty/settlement bounded evaluator | Needs v16 closure on quorum/challenge/publication.
mechanism-runtime | Theory/mechanism bounded evaluator | Needs v17 closure on publication/dispute/retirement.
spec-execution | Constitution self-hosting helper surfaces | Needs end-to-end admission/veto/challenge closure.