## Issue Matrix
ID | Source | Priority | Title | Area | Status | Note
LIB-001 | GPT-5.4 | P0 | Governance gate is observational and fail-open | Governance | open
LIB-002 | GPT-5.4 | P1 | Closeout claim narrower than workspace | Ops/Truth | open
LIB-003 | GPT-5.4 | P1 | Root-level packet sprawl / narrative drift | Truth/Human | open
LIB-004 | GPT-5.4 | P1 | Giant crates carry disproportionate risk | Scale/Runtime | open
LIB-005 | GPT-5.4 | P2 | No workspace-level compiler lint enforcement | Ops | closed_in_recall — Recall workspace has workspace lints
LIB-006 | GPT-5.4 | P2 | Performance evidence is dev-profile only | Scale | open
LIB-007 | GPT-5.4 | P1 | No independent reproducibility harness | Ops | open
CLIB-001 | Claude | P2 | GovernanceReceipt uses String not enum for disposition | Contracts | open
CLIB-002 | Claude | P2 | ToolCtx construction via serde round-trip | Contracts | open
CLIB-003 | Claude | P1 | Constraint compilation output discarded during ingest | Governance/Runtime | open
CLIB-004 | Claude | P2 | Reranker failure has no receipt signal | Runtime | open
CLIB-005 | Claude | P1 | Governance receipt is metadata not a gate | Governance | open
CLIB-006 | Claude | P2 | Governance exceptions lack temporal validation | Governance/Security | open
CLIB-007 | Claude | P1 | Write tools shown to model without approval handler | Tools/Security | open
CLIB-008 | Claude | P2 | Memory dedup via embedding search not hash index | Runtime | open
CLIB-009 | Claude | P2 | orient() has no hard cap independent of budget | Runtime/Scale | open
CLIB-010 | Claude | P2 | FailoverProvider doesn't record provider identity | Runtime | open
CLIB-011 | Claude | P3 | Mutex poisoning recovery may use stale data | Runtime | open
CLIB-012 | Claude | P1 | 15 sibling path dependencies — reproducibility barrier | Ops | open
CLIB-013 | Claude | P3 | ExportEnvelopeV3 carries 35+ empty fields | Human | open
CLIB-014 | Claude | P2 | Capability spec claims not machine-verifiable | Ops/Truth | open

## Severity Heatmap
Lens | Truth | Contracts | Runtime | Governance | Ops | Scale | Security | Human
Type system lawyer (Claude) | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Failure semantics adversary (Claude) | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 1
Governance skeptic (Claude) | 2 | 1 | 2 | 4 | 1 | 1 | 2 | 1
Tool runtime adversary (Claude) | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2
Memory integrity auditor (Claude) | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1
Performance pessimist (Claude) | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1
Provider integration tester (Claude) | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Concurrency adversary (Claude) | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Build / dependency auditor (Claude) | 2 | 1 | 1 | 1 | 4 | 1 | 1 | 3
DARPA/CLARA reviewer (Claude) | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 2
Constitutional truth auditor (GPT-5.4) | 4 | 1 | 2 | 3 | 4 | 2 | 1 | 4
Contract/schema lawyer (GPT-5.4) | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2
Failure-semantics sadist (GPT-5.4) | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 2
Ops/release skeptic (GPT-5.4) | 4 | 1 | 2 | 2 | 4 | 2 | 1 | 3
Blast-radius pessimist (GPT-5.4) | 2 | 2 | 4 | 3 | 3 | 4 | 2 | 4
Performance skeptic (GPT-5.4) | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 2
Security goblin (GPT-5.4) | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 2
New maintainer from hell (GPT-5.4) | 3 | 2 | 3 | 2 | 3 | 3 | 1 | 5